## SPRINT1
SPRINT 1 (12.5h/person) | 19.04.2022 |  |  | 20.04.2022 |  |  | 21.04.2022 |  |  | 22.04.2022 |  |  | 25.04.2022
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status
Which language do we need? | Kabir | 0 | 0 | Kabir | 0 | 0 | Kabir | 2 | 2 | Kabir | 2.5 | 3 | Kabir | 2.5 | 2
Linux server config | Rafal | 0 | 0 | Rafal | 0 | 0 | Rafal | 2 | 2 | Rafal | 2.5 |  | Rafal | 2.5
Choose game | Liz | 0 | 0 | Liz | 0 | 0 | Liz | 2 | 2 | Liz | 2.5 | 0 | Liz | 2.5 | 0
How to verify players by IP/SIM card? | Liz | 0 | 0 | Liz | 0 | 0 | Liz | 2 | 2 | Liz | 2.5 | 0 | Liz | 2.5 | 1.5
How to upload game to server? | [6 empty] | Mimi | 2 | 2 | Mimi | 2.5 | 3
How to program in linux computers? | Zoe | 0 | 0 | Zoe | 0 | 0 | Zoe | 2 | 2 | Zoe | 2.5 |  | Zoe | 2.5
How does the connecting work? | Deep | 0 | 0 | Deep | 0 | 0 | Deep | 2 | 2 | Deep | 2.5 | 2 | Deep | 2.5 | 0
What/how to write on SIM cards? | Bia | 0 | 0 | Bia | 0 | 0 | Bia | 2 | 2 | Bia | 2.5 | 1 | Bia | 2.5 | 3
Sprint grooming | [6 empty] | Everyone | 2 | 2

## SPRINT2
SPRINT 2 (12.5h/person) | 26.04.2022 |  |  | 27.04.2022 |  |  | 28.04.2022 |  |  | 29.04.2022 |  |  | 2.05.2022
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status
Which language do we need? | [6 empty] | Kabir | 2 | 2 | Kabir | 2.5 | 3 | Kabir | 2.5 | 2
Linux server config | [6 empty] | Rafal | 2 | 2 | Rafal | 2.5 |  | Rafal | 2.5 | 2
Choose game | [6 empty] | Liz | 2 | 2 | Liz | 2.5 | 0 | Liz | 2.5 | 0
How to verify players by IP/SIM card? | [6 empty] | Liz | 2 | 2 | Liz | 2.5 | 0 | Liz | 2.5 | 1.5
How to upload game to server? | [6 empty] | Mimi | 2 | 1 | Mimi | 2.5 | 3
How to program in linux computers? | [6 empty] | Zoe | 2 | 2 | Zoe | 2.5 |  | Zoe | 2.5 | 3
How does the connecting work? | [6 empty] | Deep | 2 | 2 | Deep | 2.5 |  | Deep | 2.5
What/how to write on SIM cards? | [6 empty] | Bia | 2 | 2 | Bia | 2.5 | 3 | Bia | 2.5 | 4
Sprint grooming | [6 empty] | Everyone | 2 | 2
Read "writing on sim card" paperwork | Bia | 2 | 2
Read "writing on sim card" paperwork | Mimi | 2 | 2
Read "writing on sim card" paperwork | Rafal | 2 | 2
Read "writing on sim card" paperwork | Kabir | 2 | 2
Read "writing on sim card" paperwork | Deep | 2 | 2
Read "writing on sim card" paperwork | Zoe | 2 | 2
Explore game code | Bia | 2 | 1 | [6 empty] | Bia | 2 | 3 | Mimi | 1 | 1
Learn how to create a client server with python | [6 empty] | Mimi | 1 | 1
Learn how to connect multiple clients | [6 empty] | Mimi | 1 | 1

## SPRINT3
SPRINT 3 (12.5h/person) | 3.05.2022 |  |  | 4.05.2022 |  |  | 5.05.2022 |  |  | 6.05.2022 |  |  | 9.05.2022
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status
Team meeting | Everyone | 1 | 1
Research pong | Liz | 2 | 1 | Liz | 2 | 2 | Liz | 2 | 2 | Liz | 2 | 2 | Liz | 2 | 2
Research snake | Zoe | 2 |  | Zoe | 2 |  | Zoe | 2 |  | Zoe | 2 |  | Zoe | 2
Decide the game | Deep | 2 |  | Deep | 2 |  | Deep | 2 |  | Deep | 2 |  | Deep | 2
PuTTY linux config | Rafal | 2 |  | Rafal | 2 | 2 | Rafal | 2 |  | Rafal | 2 |  | Rafal | 2
PuTTY linux config |  |  |  | Kabir | 2 | 2
Change phone IP address | Bia | 1 | 1
Learn how to write on SIM card | Bia | 2 | 2
Learn how to write on SIM card | Kabir | 2 | 2
Learn how to write on SIM card | Mimi | 2 | 2
Learn how to write on SIM card | Rafal | 2 | 2
Learn how to write on SIM card | Jaime | 2 | 2
Connect linux server to computer | Kabir | 2 | 2
Connect linux server to computer | Mimi | 2 | 2
Connect linux server to computer | Rafal | 2 | 2
Connect linux server to computer | Jaime | 2 | 2
Explore SIM card modifier application | [12 empty] | Mimi | 1 | 1.5
How to access server online | [6 empty] | Bia | 3 | 3

## SPRINT4
SPRINT 4 (12.5h/person) | 10.05.2022 |  |  | 11.05.2022 |  |  | 12.05.2022 |  |  | 13.05.2022 |  |  | 16.05.2022
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status
Re-write project description | Bia | 2 | 1
Re-write project description | Kabir | 1 | 1
Research how to set the code on the server | liz | 1 | 1 | Mimi | 2.5 | 2 | liz | 3 | 3 | liz | 3 | 3 | liz | 3 | 3
Research how to set the code on the server |  |  |  | Rafal | 2.5 | 2.5 | Bia | 3 | 3
Research on creating an app |  |  |  | Rafal | 2 | 2.5
Research on creating an app |  |  |  | Mimi | 2 | 3
Research on creating an app |  |  |  | Zoe | 2 | 2 | Zoe | 2 | 4
Create the app | [6 empty] | Mimi | 2.5 | 2 | Mimi | 2.5 | 2.5 | Mimi | 2.5 | 2.5
Create the app | [6 empty] | Kabir | 2.5 | 2.5 | Kabir | 2.5 | 2.5 | Kabir | 2.5 | 2.5
Create the app | [6 empty] | Rafal | 2.5 | 2.5 | Rafal | 2.5 | 2.5 | Rafal | 2.5 | 2.5
Create the app | [6 empty] | Bia | 2.5 | 2.5 | Bia | 2.5 | 2.5
Deciding on the game | Bia | 1 | 2.5
Deciding on the game | Rafal | 1 | 2.5
Deciding on the game | Kabir | 1 | 2.5
Deciding on the game | Mimi | 1 | 2.5
Deciding on the game | Harvey | 1 | 2.5
Deciding on the game | Jaime | 1 | 2.5
Understanding logic for game in server |  |  |  | Kabir | 2 | 2 | Jaime | 2 | 2 | liz | 2 | 2 | liz | 2 | 2
Coding the word picker function | Harvey | 3 | 3
Coding the word checker function | Harvey | 3 | 3 | Bia | 4 | 4
Plan last sprint | [12 empty] | bia | 3 | 3

## SPRINT5
SPRINT 5 (12.5h/person) | 17.05.2022 |  |  | 18.05.2022 |  |  | 19.05.2022 |  |  | 20.05.2022 |  |  | 23.05.2022
TASK | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status | Owner | Effort | Status
Creating flask app | Harvey | 2.5 | 3 | Harvey | 2.5 |  | Harvey | 2.5 | 3 | Harvey | 2.5 | 4 | Harvey | 2.5
Creating flask app | Kabir | 2.5 | 4 | Kabir | 2.5 | 2 | Kabir | 2.5 | 3 | Kabir | 2.5 | 2 | Kabir | 2.5 | 3
Creating flask app | Rafal | 2.5 | 3 | Rafal | 2.5 | 2 | Rafal | 2.5 |  | Rafal | 2.5 | 1 | Rafal | 2.5
Deploying the app | Mimi | 2.5 | 2 | Mimi | 2.5 | 3 | Mimi | 2.5 | 2 | Mimi | 2.5 |  | Mimi | 2.5
Deploying the app | Zoe | 2.5 |  | Zoe | 2.5 |  | Zoe | 2.5 |  | Zoe | 2.5 |  | Zoe | 2.5
Deploying the app | Liz | 2.5 | 1.5 | Liz | 2.5 | 2 | Liz | 2.5 | 2 | Liz | 2.5 | 2 | Liz | 2.5 | 3
Testing/ QC | Bia | 2.5 | 2 | Bia | 2.5 |  | Bia | 2.5 | 2 | Bia | 2.5 |  | Bia | 2.5 | 3
Testing/ QC | Deep | 2.5 | 2 | Deep | 2.5 |  | Deep | 2.5 | 1 | Deep | 2.5 | 3 | Deep | 2.5
Testing/ QC | Jaime | 2.5 | 2 | Jaime | 2.5 |  | Jaime | 2.5 | 2 | Jaime | 2.5 |  | Jaime | 2.5 | 3
Presentation / documentation | Zoe | 1 | 2 | Zoe | 1 | 3 | Zoe | 3 | 4
Presentation / documentation | Liz | 1 | 2 | Liz | 1 | 3 | liz | 3 | 4 | liz | 3 | 4 | liz | 2.5 | 4
final documentation | [12 empty] | liz | 2 | 3
final documentation | [12 empty] | Harvey | 1 | 2
final documentation | [12 empty] | Kabir | 2 | 3
final documentation | [9 empty] | Bia | 2 | 1 | Bia | 2 | 3
Discuss future plans | Everyone | 1.5 | 1.5